# 02 — CRITERION A PLANNER

This is a planning document. Use the factual notes and prompts to write the Criterion A report in your own voice.

# What 7–8 requires

State a learning goal and explain the connection to personal interest.

State an intended product and present multiple appropriate, detailed success criteria.

Present a detailed plan covering all success criteria.

School guide reference: p. 9 — Criterion A 7–8 descriptor; p. 19 — Objective A checklist.

# A. Starting point / prior work

SCANCOMPASS development began independently in August 2026.

A working free passive security-assessment prototype existed before the formal PP development phase.

Supervisor confirmed on 24 September that this is acceptable if the report states it honestly.

The existing product is the baseline, not the final PP product.

Formal PP evidence from now onward should show research, planning, new development, testing, ATL use and reflection.

My own wording:

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# B. Learning goal

AI-assisted working idea — rewrite and own the final wording:

Learn how to transform an existing software prototype into a viable digital startup by learning how to identify user needs, test a product with real users, develop a monetization strategy, and improve and market a technical service based on evidence.

My final learning-goal wording:

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# C. Intended product

Working direction: develop the existing SCANCOMPASS prototype into a more startup-ready service for non-technical website owners. Preserve the free passive assessment; research and, if justified, add an extended/downloadable report, a clearer free-versus-premium offer/pricing path, and evidence-based UX improvements.

Important: the premium/report scope is provisional until research supports it.

My final intended-product wording:

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# D. Personal interest

Long-standing interest in coding/computer science.

Interest in startups and how technical ideas become products people use.

Cybersecurity is technically challenging, but a major personal interest is making complex security information understandable to non-experts.

The project combines technical development with business/product learning.

My own explanation of personal interest:

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# E. Global Context — Scientific and Technical Innovation

The project uses software to address a real cybersecurity problem.

SCANCOMPASS translates externally visible technical security findings into practical guidance.

The PP explores how an existing technical prototype can become a usable service for real users.

My own Global Context explanation:

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# F. ATL skills for intentional development

| ATL area | Specific sub-skills | How I can develop it | Evidence I should collect |
| --- | --- | --- | --- |
| Organization | Plan short/long-term work; set realistic goals; organize complex information; select/use technology effectively | Maintain action plan; revise deadlines; organize evidence; plan development/testing cycles | Updated plan, calendar, journal entries, folder structure, Git milestones |
| Critical thinking | Interpret evidence; revise understanding; evaluate solutions; troubleshoot systems/applications | Compare research/user feedback; reject weak assumptions; test alternatives; diagnose technical failures | Source comparisons, decision logs, test results, before/after changes, bug investigations |

School guide reference: pp. 15–16 — Organization and Critical Thinking ATL sub-skills.

# G. Research questions

What information do non-technical website owners actually need from a security assessment?

What makes a technical security report understandable and actionable for a non-expert?

Which features should remain free and which could reasonably belong to a premium service?

What monetization/pricing approaches are realistic for a small digital security startup?

How should I test whether users understand the product and can use the report without help?

How should I use AI coding assistants transparently while keeping my decisions, evaluation and writing my own?

# H. Criterion A draft checklist

Learning goal + explanation of personal interest.

Intended product.

Research summary.

Source evaluation.

4–5 researched success criteria + product rubric.

Detailed action plan linked to all success criteria.

Works Cited.

School guide reference: school calendar: Criterion A draft due 13 October; p. 19 checklist.