# 04 — ACTION PLAN

Keep this plan alive. If dates change, record the change and reason instead of rewriting history.

# Current constraint

The class had not properly begun the planned success-criteria research because the school laptops were unavailable due to organizational problems. ManageBac is also not fully available. The response is to keep the process locally in Microsoft files and begin reliable research after school on a personal computer.

# Personalized action plan

| Date | Task | Evidence | Linked criteria | Status |
| --- | --- | --- | --- | --- |
| 24 Sep | Formal PP baseline already established; preserve prior-product evidence; record supervisor clarification | Git tag pp-start-2026-09-24; supervisor note; screenshots | All | Complete |
| 24–28 Sep | Rewrite learning/product goals in own words; record current journal entries; prepare research questions | Student-written journal; Criterion A planner | All | In progress |
| 25 Sep–5 Oct | Begin reliable secondary research: user needs, report clarity, usability, startup validation and monetization | Research log; source evaluations; MLA data | SC2–SC5 | Not started |
| 29 Sep | Academic Integrity, AI, Turnitin and MLA lesson; update AI-use procedure based on school instructions | AI-use log; integrity journal entry; citation notes | All | Upcoming |
| 30 Sep–5 Oct | Initial primary research/problem discovery with potential users, if approved/appropriate | Anonymous notes; questions; feedback summary | SC3–SC5 | Planned |
| 6 Oct | Action plan + Process Journal Audit #1 (~5 meaningful entries guideline) | Action plan; evidence register; journal | All | School checkpoint |
| 7–12 Oct | Write Criterion A draft in own words; finalize research-supported success criteria and Works Cited | Student-written draft; final criteria; source evaluation | All | Planned |
| 13 Oct | Criterion A draft submission when school submission route is available | Submission confirmation / teacher note | All | School deadline |
| 14–19 Oct | Use feedback to freeze the first formal PP development scope | Updated scope; decision journal | All | Planned |
| 20 Oct–2 Nov | Formal product development phase begins; implement researched SCANCOMPASS improvements | Git commits; screenshots; tests; journal | SC1–SC3 | Planned |
| 3–16 Nov | User testing + evidence-based product changes; explicitly document ATL use | User-test evidence; commits; before/after screenshots | SC4–SC5 | Planned |
| 17–24 Nov | Continue development; ATL evidence; Process Journal Audit #2 (~10 entries guideline) | Journal; evidence register; progress review | All | School checkpoint |
| 1–8 Dec | Product ~80–100%; Criterion A+B draft | A+B draft; product screenshots; ATL evidence | All | School deadline |
| 9 Dec–11 Jan | Final polish, full success-criteria testing and feedback | Final testing table; feedback; screenshots | SC1–SC5 | Planned |
| 12 Jan | Final product completion; Criterion C evaluation begins | Final product; rubric evaluation; user/stakeholder feedback | All | School deadline |
| 19–26 Jan | Criterion C reflection; Audit #3 (~15 entries); poster draft | Reflection draft; journal; poster | All | School checkpoint |
| 2–9 Feb | Exhibition rehearsal + Complete A+B+C draft | Full draft; exhibition materials | All | School deadline |
| 11 Feb | Personal Project Exhibition | Display/presentation evidence | All | School event |
| 23 Feb–8 Mar | Report revisions; Audit #4; final checks | Revised report; evidence; integrity check | All | Planned |
| 9 Mar | Final submission | Final report, bibliography, Turnitin report, signed integrity declaration | All | Final deadline |

School guide reference: official calendar pp. 4–5.

# Plan-change log

| Date | Original plan | Change | Reason / evidence |
| --- | --- | --- | --- |
| 24 Sep 2026 | Begin success-criteria research during PP lessons using school laptops | Research did not properly start in class; continue after school on personal computer | School laptops were not available due to organizational problems; criteria remain provisional. |