# 09 — REPORT, CRITERIA & DEADLINES CHECKLIST

The report itself must be student-written. Use this checklist to make sure your own writing answers the criteria.

# Assessment criteria

| Criterion | What you must show | What 7–8 looks like |
| --- | --- | --- |
| A — Planning | Learning goal + personal interest; intended product + detailed success criteria; detailed plan | Explain connection to personal interest; multiple appropriate detailed criteria; detailed plan covering all criteria. |
| B — Applying skills | Explain how ATL skill(s) helped achieve learning goal and product | Detailed explanations supported with specific examples/evidence. |
| C — Reflecting | Explain project impact; evaluate product against success criteria | Explain impact and evaluate product fully using specific/measurable evidence and detailed examples. |

School guide reference: pp. 9, 12 and 17.

# Final report formatting

Written report maximum: 15 pages if there is no recording.

Font: Arial or Calibri.

Minimum font size: 11 pt.

Margins: 2 cm.

Line spacing: 1.5.

Evidence images must be visible at submitted size.

Bibliography is uploaded separately and does not count toward the page limit.

Do not include a title page unless you are willing for it to count toward the page limit.

School guide reference: p. 18.

# Key deadlines

| Date | Deadline / milestone |
| --- | --- |
| 29 Sep 2026 | Academic Integrity, AI, Turnitin, MLA; source evaluation/bibliography. |
| 6 Oct 2026 | Action plan + Process Journal Audit #1 (~5 meaningful entries guideline). |
| 13 Oct 2026 | Criterion A draft: goal, product, research summary, source evaluation, action plan, success criteria, Works Cited. |
| 20 Oct 2026 | Criterion B expectations; formal product development begins; Criterion A feedback. |
| 24 Nov 2026 | ATL/Criterion B checkpoint; Process Journal Audit #2 (~10 entries guideline). |
| 8 Dec 2026 | Criterion A+B draft; product approximately 80–100% complete. |
| 12 Jan 2027 | Final product completion; Criterion C workshop and feedback collection. |
| 26 Jan 2027 | Criterion C reflection work; Process Journal Audit #3 (~15 entries guideline); poster draft. |
| 9 Feb 2027 | Complete A+B+C draft report. |
| 11 Feb 2027 | Personal Project Exhibition. |
| 23 Feb 2027 | Report revisions; Process Journal Audit #4. |
| 9 Mar 2027 | Final report submission + bibliography + Turnitin Originality Report + signed Academic Integrity Declaration. |

School guide reference: official calendar pp. 4–5.

# Before submitting any report section

Is this paragraph actually written by me?

Can I explain every claim without relying on an AI draft?

Have I cited the real sources I used?

Have I separated prior August work from formal PP work?

Have I used specific evidence/examples rather than vague claims?

Have I explained why decisions changed when evidence contradicted my first idea?

Have I disclosed AI use according to the school's latest rules?